Supplemental Materials & Methods
EoE pMHC-II Nanoparticle Therapeutics

## Table S1: Epitope Selection Metrics & Validation Status

| Allergen | Epitope Sequence | Core Region | IC50 (nM) | IEDB Rank (%ile) | MHC Allele | Tetramer Validated | Phase 1 Plan |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dairy | KIHPFAQTQSLVYPF | FAQTQSLVY (aa 59–78) | 16.78 | 0.94 | HLA-DRB1*07:01 | Yes (eoeTCR-4) | ELISPOT, TCR-seq |
| Wheat | SRCQAIHNVVHAIIL (original) | HNVVHAIIL (reframed) | 35.01 | 0.49 | HLA-DRB1*07:01 | No | ELISPOT, TCR-seq |
| Soy | AYPFVVNATSNLNFL | FVVNATSNL (aa 344–358) | 50.31 | 0.76 | HLA-DRB1*07:01 | No | ELISPOT, TCR-seq |

Note: Dairy epitope precursor (aa 59–78) shows ~92-fold affinity advantage over mature form (1535.53 nM). Wheat epitope reframed to cysteine-free window to avoid disulfide bond liability (original 6.36 nM; reframed 35.01 nM; ~5.5-fold loss). All epitopes restricted to HLA-DRB1*07:01 (30–35% EoE patient frequency). Multi-HLA expansion (DQ2/DQ8/DQ5/DR4) planned Phase 1, weeks 1–4.

## Table S2: AlphaFold2 Structural Prediction Metrics

| Construct | Format | pLDDT (Overall) | ipTM (Interface) | Mean PAE (Å) | Max PAE (Å) | RMSD to PDB 1S9V (Å) |
| --- | --- | --- | --- | --- | --- | --- |
| Dairy pMHC-II | Complex | 0.859 | 0.872 | 1.8 | 3.2 | 1.2 |
| Wheat pMHC-II | Complex | 0.884 | 0.896 | 2.1 | 3.8 | 1.4 |
| Soy pMHC-II | Complex | 0.878 | 0.891 | 1.9 | 3.5 | 1.3 |
| Dairy Single-Chain | Single-chain | 0.824 | N/A | N/A | N/A | 1.5 |

Note: pLDDT >0.70 = high confidence; ipTM >0.80 = reliable interface prediction. All complexes exceed confidence thresholds. PAE <5 Å considered acceptable for structural biology applications.

## Table S3: Nanoparticle Design Specifications

| Parameter | Value | Rationale / Notes |
| --- | --- | --- |
| Core Material | Fe₃O₄ (magnetite) | FDA-approved; biodegradable; precedent in vaccine delivery (refs) |
| Core Diameter | 20 nm | Optimal for splenic retention & antigen presentation; <100 nm avoids renal filtration |
| Surface Coating | PEG₂ₖ-maleimide | ~75 maleimides/NP; enables stoichiometric conjugation; 2 nm spacing |
| pMHC per NP | 5 copies | 5.97% surface occupancy; 5.8 nm inter-epitope spacing (optimal for TCR engagement) |
| Linker Length | 2 nm | Balances steric accessibility & stability; preserves MHC-peptide binding groove |
| Avidity Gain | ~24-fold | Relative to monovalent epitope; within published optimal (10–50×) for Tr1 priming |
| Thermal Stability | >60°C (DSF Tm) | Supports 2–8°C long-term storage; compatible with freeze-thaw (Phase 3 testing) |
| Manufacturing | Batch scalability | NP synthesis: gram scale; pMHC expression: mammalian (CHO) or E. coli (>50 mg/L target) |
| GMP Path | CMC pre-work Phase 4 | Process development & qualification (weeks 43–72); critical quality attributes (CQA): size, PDI, endotoxin, sterility |

## Table S4: 5-Phase Preclinical Development Roadmap (18–24 Months)

| Phase | Timeline (Weeks) | Primary Objectives | Go/No-Go Criteria | Budget Range | FTE Required |
| --- | --- | --- | --- | --- | --- |
| Phase 1 (Ex Vivo + Phase 1b In Vivo) | 1–14 | Ex vivo: Dairy epitope Tr1 induction (IL-10+ CD4+ ≥30% in EoE patients, n=20). Phase 1b: Single-dose NP dosing (n=5–10 mice); proof-of-mechanism (esophageal eosinophil reduction ≥50%). | Dairy IL-10 responders ≥30%; wheat/soy functional validation in ≥20% cohort. Phase 1b: Esophageal eosinophils reduced ≥50% vs. control. | $40–65k | 0.5 clinical, 0.3 lab |
| Phase 2 (Murine Efficacy) | 15–26 | House dust mite/allergen sensitization model; dose-response; kinetics of Tr1 expansion & eosinophil suppression. | Dose-response curve achieves ≥70% eosinophil reduction at optimal dose; Tr1 expansion sustained ≥8 weeks. | $35–55k | 0.3 immunology, 0.2 animal |
| Phase 3 (GLP Toxicology & Safety) | 27–42 | Acute/subacute toxicity (14-day, 28-day); biodegradation (iron-oxide organ burden, 6-month timescale); anti-drug/anti-NP antibodies. | No major organ toxicity; no unacceptable anti-NP IgE response; iron biodegradation kinetics characterized. | $105–170k | 0.5 tox, 0.3 CMC |
| Phase 4 (CMC & GMP Readiness) | 43–72 | Manufacturing process development & scale-up; stability testing (6–12 months); characterization (size, PDI, endotoxin, sterility). | GMP batch release criteria met; stability ≥12 months at 2–8°C; ≥3 batches qualify for IND use. | $80–140k | 0.5 QA/QC, 0.3 manufacturing |
| Phase 5 (Regulatory & IND Prep) | 73–84 | Pre-IND package assembly; FDA Pre-IND meeting (month 10–12); breakthrough designation application (if Phase 1b efficacy strong). | FDA Pre-IND feedback received & incorporated; IND submission-ready package. | $15–27k | 0.3 regulatory, 0.2 clinical |

Budget Reconciliation Note: Phase 1 budget increased from $20–35k (Phase 1a ex vivo only) to $40–65k (Phase 1a ex vivo n=20 + Phase 1b exploratory in vivo n=5–10) per peer review recommendation for proof-of-mechanism signal. Total preclinical budget updated from $255–427k to $275–457k. Multi-HLA expansion (weeks 1–4) included in Phase 5 regulatory costs.

Total preclinical cost estimate: $275–457k (base $275k; contingency +$182k for manufacturing delays or additional GLP studies). Timeline assumes sequential phases with minimal overlap; parallel multi-HLA epitope design (weeks 1–4) adds no cost.

## Table S5: Risk & Feasibility Matrix

| Risk Category | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Wheat/Soy Phase 1 Failure | Moderate | High | Accelerate multi-HLA design now; single-allergen (dairy) product viable for Phase 2 if wheat/soy fail. |
| NP Manufacturing Yield <10 mg/L | Low-Moderate | High | CMO scouting now; backup conjugation chemistry (SpyTag); Phase 4 gate: ≥50% yield on pilot batch. |
| Phase 1 CD4+ IL-10 <30% | Moderate | High | Phase 1b in vivo arm becomes critical; dose escalation or Tr1-adjuvant (IL-15, IL-33) contingency. |
| Anti-NP IgE in >20% Phase 1 patients | Low-Moderate | Moderate | Patient selection & desensitization protocol Phase 1b; pivot to non-iron-oxide scaffold if severe. |
| FDA Combination Product Classification | Moderate | Moderate | Budget +$30–50k; mitigate via Pre-IND meeting; negotiate "minimal CMC at IND vs. Phase 2 IND." |
| Iron Biodegradation Slower than Expected | Low | Moderate | Phase 3 GLP extended (6–12 months); may delay Phase 4 timeline +8–12 weeks. |
| Biotech Partner Not Found | Low-Moderate | Moderate | Publication + white paper accelerates licensing; Breakthrough designation improves commercial appeal. |